## Slide 1
30th April. Re-implement
Package by Gould[2].
14th June. Finish Convex Optimization Reading
Research Session
Start
Catching Up Session Start
1st Feb.
5th July. Finish Pseudo-Boolean Survey
25th July. Finish related work searching & studying.
15th Sep. Draft of project report.
10th Oct. Finish project report.
15th Oct. Finish presentation preparation
Project End